# Selecting indicators: Criteria

## SMART criteria

The desired properties of indicators will depend very much on the approach adopted and of the nature of the project.  A widely used acronym to summarise characteristics of good indicators is “SMART”.

- Specific

- Measurable (and also reliable, comparable and contextually appropriate)

- Achievable (and also cost effective)

- Relevant

- Time-bound (and also sensitive).

Additional criteria can be related to the SMART as indicated below.

|  | ### examples | ### notes on crisis ### and unstable contexts |
| --- | --- | --- |
| ### Specific |  |  |
| When indicators measure what they claim to measure and are not confounded by other factors. This is also referred to as “validity”. The problem of different meanings comes up when establishing qualitative scales of measurement. It is also an issue when designing data-collection tools for indicators. Even words such as “family”, “household”, “child”, are very culturally and contextually biased. | For example, standard weight-for-age and height-for-age measures are valid indicators of nutrition status, but are not valid measures of food security (disease being an important confounding factor). | In crisis, where there is high turnover of personnel, ill-defined indicators could result in misinterpretations or inconsistencies. |
| ### Measurable |  |  |
| Indicators must be precisely defined so that their measurement is unambiguous. This generally means quantitative (percentage, ratio, number), but can also mean qualitative. | For example, an environment might be categorised simply according to variance from normal flooding and dry seasons; drinking-water quality is often measured by categorisation according to type of source. | In crisis contexts, it is still important that indicators are measurable, but often the precision of indicators is reduced. In the immediate response after a crisis, decisions on programme response can’t wait for very precise data. See core content sheet: Selecting indicators: Levels of precision. |
| ### Reliable |  |  |
| The results should be the same regardless of who collects the data or when the measure is repeated. Also referred to as “verifiability”. | For example, weight-for-height measures are reliable measures of status of nutrition, while Middle Upper Arm Circumference measures (MUAC) are more difficult to repeat reliably. |  |
| ### Comparable |  |  |
| Indicators that allow comparison over time and also from one location to another (essential where they must help prioritise the level of need). Usually, if the indicator is reliable or verifiable, it is comparable. However, this is usually most challenging with qualitative indicators. | For example, when an indicator for participation that is reliable for measuring change over time is carried out by that local population, it may not be comparable from one programme location to another. Managers at a higher level may need to settle with a broader proxy indicator to allow comparison across project locations, for example, whether populations reported an increase in participation. | Comparability should allow for comparison with the pre-crisis situation (i.e. to facilitate a distinction between problems due to the crisis and chronic problems prior to the crisis) and with the situation in other locations (prioritise needs among population groups). |
| ### Contextually appropriate |  |  |
| The measurements used must be culturally/socially/politically acceptable to the population under study, otherwise they will likely seek to misrepresent information, under- or over-reporting events, or undermining “true” measures. | For example, direct questions about household income and assets are often considered intrusive and will yield under- or over-reporting depending on the context. | Consider also the security condition vs. the appropriateness of indicators. |
| ### Achievable/Feasible |  |  |
| The required data can actually be measured and collected. Feasibility should also be examined in terms of institutional capacity: Are the agencies, organisations, and specific staff to be involved in data collection able and willing to do so? If indicators are part of a monitoring system, can they be integrated easily into programme staff’s ongoing work? | For example, ease of sample selection, availability of specialised personnel, availability of transport | In crisis contexts, ease of sample selection, availability of transport, access, and security are crucial factors to consider. Consider that availability of personnel can be limited. |
| ### Cost-effective |  |  |
| The cost of data collection is affordable and worthwhile. | For example, capital costs, recurring costs, and personnel |  |
| ### Relevant |  |  |
| The indicators must provide information useful to the programme/project objectives and help guide decisions that key users will need to make. | For example, indicators are not relevant if they are chosen without reference to decision-makers’ needs. | In crisis context, effective coordination of M&E with operations is key. Selecting relevant indicators is an important step in achieving such coordination. |
| ### Time bound |  |  |
| Indicators should describe when change is expected. An indicator needs to be collected and reported at the right time. | For example, an indicator that can tell you only at the end of a project whether you succeeded in meeting certain objectives cannot influence the decision making process. | Timeliness of indicators is of key importance in a changing context. |
| ### Sensitive |  |  |
| Can data be collected in a timely manner? Indicators quickly reflect changes in the situation. They must correspond with the frequency of information required for decision-making. | For example, maternal mortality measures are not sufficiently sensitive for programme decisions, so process indicators are used as proxy measures. | In crisis and unstable situations, timeliness is important. Indicators should quickly reflect changes in the situations. They should be integrated in an ongoing monitoring process. Frequency and modalities of data collection should be devised to correspond with the frequency of information required for decision-making. |

Source: Adapted from ITAD, 1992:15, WHO, 1996:19.

## SPICED criteria

Another set of characteristics, SPICED, relates to the process of defining and measuring indicators for change.

|  | ### notes on crisis and unstable contexts |
| --- | --- |
| ### Subjective |  |
| Informants have a special position or experience that gives them unique insights that may yield a very high return on the investigators time. In this sense, consider what may be seen as critical data because of the source value. | Especially in complex crisis, when views can be partial and polarised, it is very important to ensure that bias will not leak in. Also note that the sudden changes provoked by a crisis may imply that the experience of informants cannot anymore be applicable to all aspects of the current situation. Consider the role of key informants |
| ### Participatory |  |
| Indicators should be developed together with those best placed to assess them. This means involving a project’s primary stakeholders, but it can also mean involving local staff and other stakeholders. | This is equally important in M&E of humanitarian response particularly though it requires preparation, longer-term presence of organisations involved in collecting data and careful approach. |
| ### Interpreted and communicable |  |
| Locally defined indicators may not mean much to other stakeholders, so they often need to be explained. |  |
| ### Cross checked and compared |  |
| The validity of assessment needs to be cross- checked by comparing different indicators and progress and by using different informants, methods, and researchers | This is all the more critical where the bias of sources can be very polarised, and where data sources and methods can be limited by logistics. |
| ### Empowering |  |
| The process of setting and assessing indicators should be empowering in itself and allow groups and individuals to reflect critically on their changing situation. | The degree to which this can be achieved in the peak of a humanitarian crisis will depend very much on the basis laid with populations prior to the emergency. |
| ### Diverse and disaggregated |  |
| There should be a deliberate effort to seek out different indicators from a range of groups, especially men and women. The information needs to be recorded in such a way that these differences can be assessed over time. | This is all the more important where the differential impact of crisis will often be related to gender, age, ethnicity, etc. |

Source: Adapted from Roche 2000.